## Links
https://docs.google.com/spreadsheets/d/1dA0qEmQ9IbtvhpPgeAN4dMN-43ixqB-qEBBAKfUETdg/edit?usp=sharing

## Scrum Meetings
Scrum Meetings
Daily Standup: Each team member shares progress, plans, and blockers.
Sprint Review: At the end of each sprint, demo completed features to stakeholders.
Sprint Retrospective: Discuss what went well, what didn’t, and how to improve next sprint.

## Sprint Retrospective
Sprint Retrospective - Sprint 1: User Authentication & Security
Sprint Duration: May 20, 2025 – June 3, 2025
Sprint Goal: Deliver core authentication and security features to ensure safe and reliable access for users.
What Went Well
1.Secure Login Feature Delivered: Successfully implemented and tested secure login using encrypted credentials and session management.
2.OTP Integration Completed: SMS and email OTPs were integrated with the transactional flow, with 98% delivery success in UAT.
3.Password Reset Flow: Covered multiple scenarios (email link expiry, token misuse) and passed security validation.
4.Improved Test Coverage: Automated test cases covered all critical paths (90% test coverage).
5. Great Team Collaboration: Smooth coordination between backend, frontend, and QA.
What Didn’t Go Well
1.Registration Flow Delays: Delays in UI component delivery caused late integration of the registration form.
2.Security Pen Test Failures: The first round of penetration testing flagged unencoded URL parameters in login redirection.
3.Time Overrun: Two user stories (logout flow and OTP resend option) took more time due to environment configuration issues.
What Can Be Improved
1.Refine Story Estimation: Underestimated complexity of secure logout and OTP resend logic. Consider spike tasks for unclear stories.
2.Early Security Reviews: Include a mid-sprint security review to avoid last-minute pen test surprises.
3.Environment Readiness: Prepare staging environments in advance to avoid blocked QA cycles.

## Release Planning
Release Planning
First Release: Plan to include all core features (authentication, basic account management, fund transfer, transaction history, notifications).
Timeline: Estimate based on sprint velocityVP.
Subsequent Releases: Advanced features, performance improvements, user feedback enhancements.

## Roles Involved
Roles Involved
Product Owner: Sets priorities, manages backlog, interfaces with stakeholders.
Business Analyst: Gathers requirements, writes user stories.
Scrum Master/Manager: Facilitates Scrum process, removes blockers.
Tech Architect: Designs system architecture.
Development Team: Implements features.
Testing Team: Ensures quality via testing.
Operations: Manages deployment and maintenance.